## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Dark
PROJECT: CMPG 315 : Network Project
CMPG 315 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Group 04
Project start date: | 2024-03-04 |  |  |  |  | March | [13 empty] | April | [27 empty] | May
Scrolling increment: | 20 | time axis 2024-03-24 to 2024-05-18
Milestone description | Category | Assigned to | Progress | Start | Days | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Group Task 1: Reflections | Goal |  | 100% | 2024-03-04 | 25.2 | S: 2; M: 2; T: 2; W: 2; T: 2
Do course work | Low Risk | All Members | 100% | 2024-03-04 | 3
Write reflections for course work and send/ upload to GitHub. | Milestone | All Members | 100% | 2024-03-07 | 1
Timeline for project | Low Risk | Group Leader | 100% | 2024-03-04 | 2
Summary of work ethic | Low Risk | All Members | 100% | 2024-03-04 | 1
Compile draft documentation | Milestone | Group Leader | 100% | 2024-03-13 | 2
Group Task 2: Continuous Reporting | Goal |  | 100% | 2024-03-04 | 73 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Notes and Attendance | High Risk | Group Leader | 100% | 2024-03-04 | 73
Record of assigned tasks etc. | High Risk | Group Leader | 100% | 2024-03-04 | 73
Group Task 3: Topology Network design | Goal |  | 100% | 2024-04-11 | 26 | T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2
Complete network designs for rooms on Packet Tracer. | Milestone | All Teams | 100% | 2024-04-11 | 6 | bar: T to T
Send Packet Tracer files to Team 3 | Low Risk | All Teams | 100% | 2024-04-17 | 1
Compile and test packet tracer files | Milestone | Team 3 mainly | 100% | 2024-04-18 | 3 | bar: T to S
Describe network topology design | Milestone | Team 3 mainly | 100% | 2024-04-21 | 2 | bar: S to M
Finalization of relevant documentations | Milestone | Team 3, Group Leader | 100% | 2024-04-23 | 3 | bar: T to T
Group Task 4: Text Messaging Application | Goal |  | 100% | 2024-05-07 | 9 | T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2
Research and Tests | On Track | Selected Developers | 100% | 2024-04-11 | 12
Design Application | On Track | Selected Developers | 100% | 2024-04-23 | 6
Test concept | On Track | Selected Developers | 100% | 2024-04-29 | 2
Assign Front, Back, Back/ Front -End roles to members and start developing | Milestone | All Members | 100% | 2024-05-01 | 3 | bar: W to F
Merge the Front-and Back End files | Milestone | Selected Developers | 100% | 2024-05-04 | 2 | bar: S to S
Test the application | Milestone | Back/ Front-End Dev | 100% | 2024-05-06 | 1 | bar: M
Finalize application and optimize | Milestone | Back End Dev | 100% | 2024-05-07 | 3
Double check | High Risk | All members | 100% | 2024-05-10 | 3
To add more data, Insert new rows ABOVE this one

## Light
PROJECT: Light
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Riku Nakano
Project start date: | 2024-05-15 |  |  |  |  | May | [13 empty] | June | [27 empty] | July
Scrolling increment: | 5 | time axis 2024-05-20 to 2024-07-14
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-05-20 to 2024-07-14
Project development
Project charter | Goal | Name | 25% | 2024-05-15 | 3
Research | Milestone |  |  | 2024-05-20 | 1 | bar: 2024-05-20
Projections | Low Risk |  | 50% | 2024-05-12 | 10
Stakeholders | Milestone |  |  | 2024-06-04 | 1 | bar: 2024-06-04
Review | Med Risk |  | 10% | 2024-05-21 | 6
Contracts
Proposals | High Risk |  | 60% | 2024-05-21 | 13
Document review | On Track |  | 50% | 2024-05-23 | 9
Bid date | Low Risk |  | 33% | 2024-05-28 | 11
Award date | Milestone |  |  | 2024-05-30 | 1 | bar: 2024-05-30
Finalize |  |  |  | 2024-05-31 | 24
Design
Feasibility study | On Track |  |  | 2024-05-30 | 4
Submit permit applications | Med Risk |  |  | 2024-06-02 | 14
Design proposal | On Track |  |  | 2024-06-17 | 6
Materials | Goal |  |  | 2024-06-21 | 3 | 2024-06-21: 2; 2024-06-22: 2; 2024-06-23: 2
Equipment | Low Risk |  |  | 2024-05-21 | 19
Testing
Environment |  |  |  | 2024-06-24 | 15
System test |  |  |  | 2024-07-08 | 5
Issues/bugs | Milestone |  |  | 2024-08-19 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2024-05-15 |  |  |  |  | May | [13 empty] | June | [27 empty] | July
Scrolling increment: | 5 | time axis 2024-05-20 to 2024-07-14
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-05-20 to 2024-07-14
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-15 | 3
Task 2 | Milestone |  |  | 2024-05-20 | 1 | bar: 2024-05-20
Task 3 | Low Risk |  | 50% | 2024-05-12 | 10
Task 4 | Milestone |  |  | 2024-06-04 | 1 | bar: 2024-06-04
Task 5 | Med Risk |  | 10% | 2024-05-21 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-05-21 | 13
Task 2 | On Track |  | 50% | 2024-05-23 | 9
Task 3 | Low Risk |  | 33% | 2024-05-28 | 11
Task 4 | Milestone |  |  | 2024-05-30 | 1 | bar: 2024-05-30
Task 5 |  |  |  | 2024-05-31 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-05-30 | 4
Task 2 | Med Risk |  |  | 2024-06-02 | 14
Task 3 | On Track |  |  | 2024-06-17 | 6
Task 4 | Goal |  |  | 2024-06-21 | 3 | 2024-06-21: 2; 2024-06-22: 2; 2024-06-23: 2
Task 5 | Low Risk |  |  | 2024-05-21 | 19
TITLE 4
Task 1 |  |  |  | 2024-06-24 | 15
Task 2 |  |  |  | 2024-07-08 | 5
Task 3 | Milestone |  |  | 2024-08-19 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one