## Members
Student Number | Name | Surname | Role
41093615 | Andre | Pretorius | Team 2
37328409 | Anri | van Tonder | Team 5
38566567 | Ariël | Truter | Team 4
40513262 | Christian | Coetzee | Team 5, Group Leader
41049764 | Danika | le Roux | Team 1, Takes Attendance
41293584 | Henk | Mooiman | Team 3
44214987 | Jacques | Cloete | Team 1
40779173 | Jean-luc | Bégué | Team 2
40977676 | Maderi | de Meyer | Team 4
37943278 | Waldo | Nieman | Team 3

## Task Allocations
TEAMS
Packet Tracer Tasks | 1 | 2 | 3 | 4 | 5
13 Offices
Technicians' Office
Reception/ Waiting Area
Kitchen
Meeting Room/ Board Room
Machine Room/ Server Room
Open Floor Space

## Project Timeline
Activity | Start Date | End Date | Amount of days | Contigency Day(s) | Final End Date | Due Date | Notes
Group Task 1: Course work | 2024-03-04 | 2024-03-25 | 21 | 4.2 | 2024-03-29 04:48 | 2024-03-29 | Most of the member's reflections were received on time. But also difficult as some members were on vacation or busy with work during the recess. But everyone managed to submit their reflections on time for compiling it all in one document.
Group Task 1: Documentation Draft | - | - | - | - | 2024-03-29 04:48 | 2024-04-08 | We had a meeting and reviewed the document, especially the ethics and timeline of the project.
Group Task 3: Topological Network Design | 2024-04-11 | 2024-04-20 | 9 | 1.8 | 2024-04-21 19:12 | 2024-04-19
| 2024-04-22 | 2024-05-11 | 19 | 3.8 | 2024-05-14 19:12 | 2024-05-16
|  |  | 0 | 0 | 0
Formulas:
Amount of days = DAYS([End Date],[Start Date])
Final End Date = [End Date]+[Contigency Day(s)]
Final End Date = [Final End Date, row above]
Note on C5: christian coetzee: was 5